BPA Tasks for Admissions

Updated: December 7, 2012

| Opportunity | Task | Responsible (Name in bold is lead) | Due Date | Priority | IT Implications | Notes | Status |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Refine and Improve Communications with Staff | Draft new CCC Apply Page | Dottie | 4/30/12 | High | No |  | Complete |
|  | Draft new welcome page/message for exempt and non-exempt students | Sue, Arlene | 4/30/12 | High | No | Text from colleges completed; single sign on planned for spring, 2013 | Complete |
|  | Draft new registration message for continuing students | Arlene | 4/30/12 | High | No |  | Complete |
| Clarify and agree on criteria used to determine residency | Schedule meeting with Kim , John, Cheq, Vivien and Cass Cass to document process | Henry | 4/30/12 | High | No |  | In Progress |
| Reduce the number of applications that need manual review (SWACCAP) | - Conduct root cause analysis – gather statistics - Determine if any can be automated – different filters on Common Matching | Henry/Edgar | May, 31, 2012 | High | Yes | First phase of this review completed; Edgar has snapshot; Convene small group to examine. Add to ESC agenda to prioritize | In Progress |
| Automate failed prerequisite process | - Automate the dropping and notification process - Include student’s name and the dropped course(s) in the email message | Joyce, Shell, Arlene, Sue, Maria and Ruth | June, 2012 | High | Yes | Implement with spring, 2013 registration | In Progress; Joyce sent test instructions to Arlene, Sue and Ruth; we’ll make sure it’s working and plan to go live for failed prerequisites at the end of the fall semester. |
| Implement Work Flow Project | - Contact another user of workflow for information - Select one paper process to implement | Eric, VPSSs | May 31, 2012 | High | Yes | The technology is there, but we will need outside help. May want to develop a library of workflow projects. Bring to ESC to prioritize |  |
|  | Schedule Extender Training | Edgar | May 31, 2012 | High | No | Session scheduled for May 18 1-3 p.m. CSM 1-140 Skyline will barcode old files | Completed; Continue to schedule as needed |
|  | - Implement WebSMART web application for graduation process - Use ARGOS for extracts, lists, labels - Configure WebSMART - Execute local mods for colleges | Eric, Niruba | March, 2013 | High | Yes | Pilot with December 12 grads? | Completed the pilot project. |
|  | Determine automated method for assessing institutional SLOs for grads | Eric, Henry | Dec., 2012 | High – Accreditation Impact | Yes | CSM uses existing survey for 2012 grads | Completed for summer, 2012. |
|  | Improve WebSMART transcript request page- all on one page, fewer options, reduce/clarify text | Jose, Edith, Jeremy | 4/30/12 | Medium | Yes – programming changes is significant workload for ITS; may need to build inside WebSMART | Text has been modified; ITS will need to program change | In Progress |
| Improve concurrent enrollment process | - Review regs – course restrictions - Develop overarching strategy - Negotiate agreement on admission to the concurrent enrollment “program” rather than specific courses - Identify groups of students to recruit (underperformers, high achievers) - Create plan to cultivate relationships with high schools - If restricting courses, use Banner to enforce rather than manual check - Explore bar coding and imaging form | Jennifer, VPSSs | May, 2012 | Medium | Yes | BPA conducted on October 31st. Utilize results to streamline processes. | In Progress |
|  | - Identify “touch points” with faculty; conduct focus groups - Waitlist process through add/drop; discontinue use of auth codes - Late submission – census, incomplete grades, grades | VPSSs, VPIs | August, 2012 | Medium | Yes |  |  |
|  | Push out Degree Works to students | Deans of Counseling, Public Relations Directors | May 31, 2012 | High | Yes | Wait until SEP component is functional; Edgar to attend May 11 ESC meeting to update committee | In Progress About 30 counselors per day are using; Student use about 175-200 per day. |
|  | Instruct students to send transcripts from other schools | Henry, Kim, John, Registrars | TBD | Medium | No | Wait to implement when Transcript Articulation Project underway; All ASSIST data has been loaded in production | In Progress |
|  | Develop A&R operations guidelines; post to Sharepoint or wiki | Henry, Kim, John, Joyce, Alan Miller, Researchers | July, 2012 | High | No |  | Not Started |
|  | Incoming electronic transcripts (We are using Etrans for outgoing transcripts) | Eric; Alicia, Renee, Michael | TBD | High | Yes | Some concern about EDI transcript; Need ESC to prioritize |  |